## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Indicator 1) Gender Pay Equity Employment Policy (Related) Recruitment Guideline | Policy | Provides GRV employees with clear and consistent understanding of their role and responsibilities, and that of GRV, to meet employment compliance obligations. | For Review | Yes | The policy itself has not been updated, however, a related guideline was developed to ensure clarity and consistency in process during the recruitment process for candidates and internal applicants. The Recruitment Guideline is a document created with the outcome of ensuring, "...recruitment and selection at GRV is fair to all applicants, with selection decisions based on merit". When developing this guideline, subject matter experts were consulted to ensure the guideline adhered to equal opportunity employment legislation, whilst also aligning with public sector best practice. The guideline assigns oversight responsibility to the People Services department, ensuring no recruitment occurs outside this process. To mitigate risk of bias during the recruitment process, recruitment panels aim to be 50/50 gender split.
Indicator 1) Gender Pay Equity Employment Policy | Policy | Provides GRV employees with clear and consistent understanding of their role and responsibilities, and that of GRV, to meet employment compliance obligations. | For Review | No action taken
Indicator 2 & 3) GRV Gender Compositon Employment Policy | Policy | Provides GRV employees with clear and consistent understanding of their role and responsibilities, and that of GRV, to meet employment compliance obligations. | For Review | No action taken
Indicator 4) Sexual Harassment Respect in the Workplace Policy | Policy | Provide GRV employees with a clear and consistent understanding of their role, responsibilities, and rights, and that of GRV, to foster an inclusive and diverse workplace, free of all forms of discrimination and harassment, including sexual harassment and bullying. GRV aims for equality of opportunity for all employees. | For Review | Yes | The policy was reviewed against the Respect@Work legislation and found to be compliant and appropriate. Further employee training on respect in the workplace was completed during the reporting period through the deployment of a dedicated 'respecting each other' course as part of GRV's annual required learning program.
Indicator 4) Sexual Harassment Sexual Harassment Policy | Policy | Provide GRV employees with a clear and consistent understanding of their role, responsibilities, and rights, and that of GRV, to foster a workplace free of sexual harassment. GRV aims for equality of opportunity for all employees. | For Review | Yes | The policy was reviewed against the Respect@Work legislation and found to be compliant and appropriate. Further employee training on respect in the workplace was completed during the reporting period through the deployment of a dedicated 'respecting each other' course as part of GRV's annual required learning program.
Indicator 4) Sexual Harassment Reporting Unacceptable Behaviour Guide | Policy | Ensure GRV employees and contractors understand the definitions and requirements of appropriate behaviour in the workplace, and how to report unacceptable behaviour. | For Review | No action taken | Existing procedure remains appropriate and accurate, so no action was required.
Indicator 4) Sexual Harassment Respect in the Workplace Guide | Policy | Ensure GRV employees and contractors understand the definitions and requirements of appropriate behaviour in the workplace, and how to report unacceptable behaviour. | For Review | No action taken | Existing procedure remains appropriate and accurate, so no action was required.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Prioritisation of increase in women at manager & senior specialist levels | Ongoing | The promotion of a balanced workforce is a continous goal that GRV strives for and will need to review on a continual basis. GRV continues to partner with WORK180 to understand our strengths and areas for development while increasing awareness of GRV as a potential employer of women. All job adverts are revivewed to ensure there is no gender bias using tools provided by WORK180. | GRV has been recognised by WORK180 as a top 100 employer of women. | Ongoing | People Services
Benchmarking roles at manager & senior specialist levels | Ongoing | Positions are benchmarked as they are are created, when there is a major change, or in readiness for recruitment. Progression is affected by the fact most positions are covered by an enterprise agreement which determines the classification and progression of employees. For graded positions, pay is equal for all persons doing that work. |  | Ongoing | People Services
Performance & development, process improvement & manager upskilling | Ongoing | Employees are supported to upskill via external training, supported study leave and required learning provided by GRV. This will continue as requested/ required for employees. GRV continues to support employee development through a range of programs. All employees are eligible for development. During the reporting period, GRV began tracking and reporting on learning hours via the people dashboard. Additionally, GRV rolled out both required learning (in the areas of keeping you safe, respecting each other, working ethnically and sustainably, and safeguarding information) to all employees and navigating conflict training to frontline employees. | Visibility of learning hours via the people dashboard | Ongoing | People Services
Education to build awareness (gender composition) | Ongoing | Education and awareness are always continuing due to employees joining and leaving the organisation. Reports are available on teams to managers as they request them. | GRV continues to report on gender composition monthly via the people dashboard and regularly to the People & Culture Committee of the Board via the people scorecard. | Ongoing | People Services
Workplace behaviours | Ongoing | Required learning promoting respect in the workplace is assigned to all employees through GRV's HR Information System. Dedicated investigation processes are in place when incivility/anti-social behaviour is reported. The required learning program is delivered annually to all employees. Each year the program undergoes a review and refresh to ensure it remains relevant and current. Each course includes modules to explain key concepts coupled with a task to confirm relevant policies and procedures have been read and understood plus a team discussion to explore how those concepts apply on a daily basis. Additionally, policies and procedures are being progressively updated to include a dedication 'speak up' section so that it's clear to employees how and when they can raise concerns regarding workplace behaviours. GRV is also actively reviewing its values set to ensure the values and corresponding behaviours are fit for purpsoe and support our cultural aspirations and strategic objectives. | * Delivery of the required learning program * Implementation of the values refresh program | Ongoing | People Services
Improve data collection | Ongoing | Data collection has improved since the GEAP with the continued implementation of GRV's HR Information System. This includes the adoption of required tasks for new employees to complete diversity questions, which are then available to analyse via reports. Plans to create an instantly accessible dashboard for all leaders is underway. This will make these aspects of their teams readilly available when they log into the system's homepage. | Implementation of diversity questions
Education & training (sexual harassment) | Ongoing | Respecting each other is a required learning course which was launched in 2023. This is mandatory for all employees to complete on an annual basis. Frontline employees undertook a Confidently Navigating Conflict training in 2022-2023.
Making reporting easier (sexual harassment) | Ongoing | Promotion of the Speak Up program in partnership with YourCall continues, in addition to other channels. There are hirearchies within departments which may be preventing all reports of harassment to be appropriately managed. There is continued work in this space to develop easy, immediate incident reporting. Additionally, policies and procedures are being progressively updated to include a dedication 'speak up' section so that it's clear to employees how and when they can raise concerns regarding workplace behaviours.
Transparency in process for complainants, ensuring support (sexual harassment) | Ongoing | There is ongoing planning with external support to develop transparency in these processes moving forward. This agency is also working to develop ways in which GRV can better support victims of harassment. | Increase in the number of internal candidates
Internal promotion of job/career opportunities | Ongoing | Weekly career opportunities are sent out to all GRV employees. Employees are encouraged to apply for any position which is advertised both internally and externally. An evergreen expression of intererst application is always present on the career's page on the GRV website.
Diversity in selection panels | Ongoing | Currently selection panels aim for a 50/50 gender split. The pool of gender diverse identifying people is currently too small to also include on panels (not necessisarly appropriately qualified to evaluate particular positions).
Hiring manager upskilling | Ongoing | Employees are supported to upskill via external training, supported study leave and required learning provided by GRV. This will continue as requested/required.
Structured approach to succession planning & promotions | In progress | Work is underway to configure the Succession module within GRV's HR Information System. Once configured, GRV will undertake a talent management and succession planning process with the Leadership Team to identify key persons, critical roles, and potential as well as developing a succession plan.
Regular review of leave type options | In progress | GRV are currently at enterprise bargaining for both enterprise agreements (GRV Employee Enterprise Agreement 2023-2024 and GRV Stewards and Associated Employees Enterprise Agreement 2020-2024). Additional leave types may be discussed, however, GRV is restricted in what it can offer due to the requirement to stay alligned with what the Public Sector currently offers.
Further employee education to better understand entitlements | Ongoing | Enterprise agreements are readily available to all employees via GRV's intranet. Additionally, GRV have developed and implement guidelines, procedures, and help cards to support employees. Employees are encouraged to reach out to People Services when they have any questions. People Services meet with all new starters within their first week/at their first probation check in, which is another opportunity to let employees know where they can access this information. During bargaining periods, there is regular communication and promotion of entitlements.
Ensuring single point failure is negated to enable employees the freedom to take leave with confidence | Ongoing | Managers are encouraged to reach out to People Services if they have concerns around servicing during an employee being on leave. Temporary support has been utilised in the past to ensure continued service delivery.
Ensuring continued flexibility & hybrid workplace practices | Ongoing | GRV supports flexible working arrangements as per legislation. GRV also promotes being a hybrid workplace. | Increase in the number of flexibility working arrangements in use
Respectful behaviours embedded | Ongoing | Embedding behaviours is ongoing as employees join and leave the organisation. Continued required learning and promotion of organisation values through recent Cascade Workshops (values refresh) is essential in achieving this goal long term.
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1: Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Accountability for the delivery of the GEAP rests with the People Services department which includes six resources: the Head of, two Leads, two Coordinators, and a Health Safety Wellbeing specialist. People Services organises its work using the portfolio model, with gender equality forming part of the communications and engagement portfolio. Each portfolio has a dedicated owner who is accountable for the design and execution of activities within scope together with all relevant artefacts, processes, and resources. The portfolio owner for communications and engagement is one of GRV's two People Leads (formerly People & Culture Business Partner) which is a full time, ongoing position. Portfolio owners may utilise internal resources (such as colleagues, working groups, people leaders/managers) or external resources (e.g. suppliers, public programs) in the delivery of activities within scope. Portfolio owners report on their progress quarterly via the People Services team day. Highlights also form part of the monthly CEO's report with detailed reporting to the People & Culture Committee through their regular meetings.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | No | Indicator 2 & 3: GRV Gender Composition There are fluctuations in gender composition across all areas of GRV since the release of the 2021 GEAP. Some of this can be attributed to continued efforts to boost female or male employees in certain areas, while other figures are representative of either natural attrition or ongoing efforts to optimise the organisational structure. Overall, GRV experienced a slight shift since the release of the 2021 GEAP, with women now comprising 42%, men comprising 57% and gender diverse comprising 1%. Gender breakdown by team is as follows. Customer, Marketing & Commercial: since the last reporting period, two departments came togeher. Women make up 20% of this department, while men make up 80%. Corpoate Services (which includes Legal & Regulatory Services, People Services, and Technology): LRS: Women make up 57.2% while men make up 42.8%. ¦ PS: People & Culture: Women make up 66.67%, while men make up 33.3%. ¦ Technology & Innovation: Women make up 39.13%, while men make up 60.87%. Corporate Services as a whole is made up of 55.9% men and 44% women. Participants & Strategy: women make up 50%, while men make up 50%. Finance, Infrastructure & Procurement: F&I was previously reported as women comprising 80% of the department. This has improved this period with women comprising 69%, while men make up 31%. Integrity: previously reported as women comprising 40% of the department. As of this reporting period, women comprise 32.6%, while men make up 67.4%. Racing, Racing Safety & Clubs: previously reported as women comprising 11% of the department. This has seen a drop, with women comprising 9%, while men make up 91%. Welfare & Rehoming: women make up 70.3%, while men make up 29.7%.
Gender composition of governing bodies | No | Indicator 2 & 3: GRV Gender Composition GRV is governed by a Board of Directors appointed by the Minister of Racing. At the time of the submission of the GEAP, there was a 50/50 gender split of the Board. As of this reporting period, the Board appointed another member, resulting in an odd number of Board members. As of this reporting period, the Board leaned in favour of male appointees.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Indicator 1: Gender Pay Equity As stated in the 2021 GEAP, the largest pay disparity is at manager and senior specialist levels. This is most apparent at level 2 (direct reports of General Managers) where factors such as historic recruitment, impact of parental leave, and unconcious bias when considering development opportunities for employees can affect pay outcomes. Positions at this level are generally salaried. Senior leadership (level 1) lean positively toward female employees, indicating there is a need to professionally develop female employees below level 1. At lower levels there is less disparaity as positions generally fall under an enterprise agreement which sets pay levels and ranges. Level 1: Male average: $236,379 ¦ Female average: $272,124 Level 2: Male average: $140,652 ¦ Female average: $114,566 Level 3: Male average: $89,104 ¦ Female average: $90,157 Level 4: Male average: $80,692 ¦ Female average: $76,534 Level 5: Male average: DU ¦ Female average: DU The 2021 GEAP explored the gender pay gap within GRV and identified that there was a 12.5% gap between male and female employees. This was below the national benchmark at the time, of 15%. As of the current reporting period, GRV have had a slight decrease to 12.4%, which still remains below the current national benchmark of 13%. GRV's gender pay gap also remains lower than that of the Victorian State gap at 12.9%. We consider this an improvement on previous years, and we expect a continued reduction in this gap as we further promote development opportunites for women at GRV, and the implementation of succession planning.
Sexual harassment in the workplace | Yes | Indicator 4: Workplace Sexual Harassment During the reporting period, GRV released Respecting each other, a required learning course which covered topics relating to bullying and harassment, as per promises stated in the 2021 GEAP. GRV continued the promotion of the Respect in the Workplace Policy, Sexual Harassment Policy, Reporting Unacceptable Behaviour Guide and Respect in the Workplace Guide to all employees. People Services continues to promote positive reporting culture through the promotion of the 'speak up' program in partnership with YourCall via a weekly Wellbeing Wednesday's newsletter, which is received via email by all employees. GRV saw an Employee Assistance Program utilisaion rate of 8% during the reporting period, an improvement on previous years. This is a positive outcome for GRV, as employees continue to feel empowered to speak up and seek help when they need it. As per the People Matter Survey 2023, 24% of respondents (119 total out of 258 active employees at that time) experienced or witnessed one or more negative behavious such as sexual harassment, discrimination, bullying or agression/ violence. While steps have been taken to educate employees on respectful behaviour, further work is required at an industry level as many of our employees work in public facing roles. As per the 2023 People Matter survey results, 7% of respondants experienced sexual harassment. This is an increase from 2022 People Matter Survey results, which 5% of respondants had experienced sexual harassment. This increase may be attributed to a number of factors, such as lower rates of participation than the previous year. For example, the 2023 survey had fewer participants - in 2022, 63% of employees participated, while only 46% participated in 2023. In 2022, 16% of those that responded that they had experienced sexual harassment submitted a formal incident report. In 2023, that number increased to 43%. In comparison, the comparitor group avergae in 2023 was just 27%. These results indicate that although sexual harassment is still occurring, that employees are feeling more empowered to report this abuse, which is an excellect indicator that GRV is continuing to make positive progress in this area
Recruitment and promotion practices in the workplace | Yes | Indicator 5: Recruitment & Promotions In the 2021 GEAP, multiple improvement opportunites were identified by employees in regards to development opportunites, transparency around remuneration bands and addressing potential disadvantage in approval for development opportunities. Since then, GRV have released a Recuitment Guideline which is readily available to all employees via the home page on GRV's Intranet. The guideline was developed to ensure clarity and consistency in process during the recruitment process for candidates and internal applicants. The Recruitment Guideline is a document created with the outcome of ensuring, "...recruitment and selection at GRV is fair to all applicants, with selection decisions based on merit". When developing this guideline, subject matter experts were consulted within the organisation to ensure the guideline adhered to equal opportunity employment legislation, whilst also aligning with public sector best practice. The guideline stipulates that the People Services department is responsible for overseeing the recruitment process, and that no recruitment may occur outside this process. To mitigate risk of bias during the recruitment process, recruitment panels aim to be 50/50 gender split. GRV provides access to the GRV Employee Enterprise Agreement 2023-2024 and the GRV Stewards and Associated Employees Enterprise Agreement 2020-2024 which includes a comprehensive break down of all remuneration bands below a salaried level (salaried is in reference to senior, speciailst roles which may require variation in remuneration in order to remain competitive in the job market, attracting appropriately qualified talent). GRV's HR Information System is being maximised to ensure ROI, this has included the implementation of the Succession module, which gives managers a dedicated space to acknowledge employee's skills and nominate them for promotions to their General Managers. In the 2023 People Matter Survey, 42% of respondants agreed that the promotions process is fair (35% neither agree nor disagree) and 47% agreed that they have an equal chance at a promotion at GRV (36% neither agreed nor disagreed). This shows that there is further action needed to ensure GRV is promoting professional growth and career pathways to its employees.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | No | Indicator 6: Leave & Flexibility There is no record kept of family violence leave taken as per legislative requirements. As of the reporting period, GRV did not track the number of flexible working arrangements in place (although all employees working under such an agreement have a written agreement), however GRV actively supports flexibility as per both the GRV Employee Enterprise Agreement 2023-2024 and the GRV Stewards and Associated Employees Enterprise Agreement 2020-2024.Working arrangements supporting employees with family or caring responsibilities are supported for all employees, however there is no designated record of each arrangement currently in place. GRV aims to improve reporting as the HR Information System will replace paper-based forms, allowing GRV to track and report on flexibility requests and active arrangements. Additionally, GRV continues to practice hybrid working, providing employees with flexibility to work from home or other locations in consultation with their manager.
Gendered segregation within the workplace | No | Indicator 7: Gendered Work Segregation GRV's workplace data continues to indicate the long term effects of historic recruitment and reputation of the racing industry, as evidenced by incidents of gendered segregation. As previously reported, functions such as Finance and Clubs were male dominated although there has been an improvement with women now comprising 69%. That said, further work is needed to increase female participation in roles which have been perceived as "traditionally masculine". There has been a concerted effort to increase female representation in the Integrity function, however, this is sitting at 32% as opposed to the previously reported 40%. In 2021, GRV's workforce comprised of 43% women, 56% men and 1% gender diverse. As of the current reporting period, GRV's workforce comprises of 42% women, 57% men and 1% gender diverse. There is ongoing work required to promote women in the racing industry as a whole, and programs such as the recently deployed Certificate III in Racing Services (Track Maintenance) aims to train people who are new to the world of racing.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled